## Slide 1
DIGITAL ARENA
Presented by Sokol Ymeraj, Rishi Rajiv, Grant Schweber, Triston Wennersten, Akshit Verma

## Slide 2
Digital Arena specializes in live-streaming sports events and supports social media outreach, while also providing tools for skill development across various sports. This technology can widely be utilized in sports across multiple countries. The content can be posted on any social media platform and is valuable for community building.
EXECUTIVE SUMMARY

## Slide 3
VALUE
PROPOSITION
This is where Digital Arena has its edge in the market. Up till now, you would have had to set up hardware and then use a third-party software package to score, go live and create overlays etc. We have come up with a solution that is simple to use and affordable for everyone. Here are just a few features:
  Cloud Streaming
  Unlimited Games
  First Game Free
  iOS / Android App
  Streaming Quality upto 4K
  Scoring Overlays (Provided with clock)
  Display Streaming Partner/Sponsor logos
  Generate shareable clips
  Remote Score
  24x7 Support

## Slide 4
FUNDING REQUIREMENT
The $10 million in funding will be allocated across several key areas to ensure Digital Arena can scale efficiently and capture a significant market share. Below is the breakdown and justification of how the funds will be used:
Total Funding Request: $10 Million
Notes: Please choose a name for your group and include it in the submission. Also, please explain where are you requesting the funds from? A bank? Investors?

## Slide 5
TECHNOLOGY DEVELOPMENT– $3 MILLION
To enhance Digital Arena’s Streaming Software by improving features such as streaming quality, user interface, and integrations for more sports and devices.
⁠PRODUCT DEVELOPMENT – $2 MILLION
Introduce new features like advanced scoring analytics, AI-driven highlights generation and enhanced sponsor integration tools.
MARKETING & USER ACQUISITION – $2.5 MILLION
Build brand awareness, drive customer acquisition, and expand internationally through targeted marketing campaigns.
EXPANSION OF CUSTOMER SUPPORT– $1.5 MILLION
Develop partnerships with sports leagues, educational institutions, and media organizations.
Build a scalable 24x7 customer support team and improve operational capacity to handle a growing user base.
PARTNERSHIPS & STRATEGIC ALLIANCES – $1 MILLION

## Slide 6
Digital Arena is poised to capitalize on the global sports streaming market, projected to exceed $80 billion by 2026. Its cloud-based platform removes geographical barriers, making it accessible for professional and grassroots sports organizations worldwide. Digital Arena targets emerging markets in Asia, Africa, and Latin America, where sports participation is rising but broadcasting infrastructure is limited, offering low-cost solutions for underserved regions with growing mobile penetration. In established markets like North America and Europe, Digital Arena provides smaller leagues, schools, and semi-pro teams with affordable streaming and sponsor integration tools. Global partnerships with sports leagues, educational institutions, and media companies will drive adoption, while $10 million in funding will support localization, partnerships, and market expansion, positioning Digital Arena to capture a substantial share of the growing global sports streaming industry.
GLOBAL ELEMENT

## Slide 7
PROJECT CHARTER
  Project Title: Digital Arena
  Project Overview: The Digital Arena project aims to provide a user-friendly, cloud-based solution for live-streaming sports events.
  Purpose and Objectives:
    Provide a cloud-based streaming solution that simplifies live sports broadcasts.
    Ensure that the software is intuitive for parents and volunteers to set up and use.
    Integrate features like scoring overlays, remote scoring, and real-time clip sharing.
  Project Milestones:
    Milestone 1: Business Plan with Justification
    Milestone 2: Project Management Plan
    Milestone 3: Schedule with Critical Path Analysis
    Milestone 4: Cost Management Plan
    Milestone 5: Resources, Communication, and Risk Management Plan
    Milestone 6: Executing the Project
  Project Team: Sokol Ymeraj, Rishi Rajiv, Grant Schweber, Triston Wennersten, Akshit Verma

## Slide 8
TEAM MEMBERS
KEY STAKEHOLDER IDENTIFICATION
  Players: Individuals who play sports.
  Tournament Organizers: Responsible for organizing gaming tournaments.
  Sports: Professional teams.
  Streaming Platforms: Platforms that stream content.
END USERS
  Venture Capital Firms: Provide funding for the project.
  Investors: Individual investors who provide funding.
INVESTORS
  Traditional Sports Teams: May be interested in using the platform for events and fan engagement.
  Grassroots/ Youth Teams: May use the platform for training, competitions, and streaming of games.
SPORTS TEAMS
  Development Team: Engineers / developers responsible for building the platform.
  Marketing Team: Promotion.
  Customer Support Team: Provides support to customers.
  Designers: Ensure the platform is user-friendly.
  Legal Counsel: Provides legal advice and ensures compliance.

## Slide 9
Requirement | Priority | Stakeholder | Acceptance Criteria
Enable live streaming of sports events | High | End Uers/Sports Teams | Stream must be viewable with clear quality on mobile devices
Integrate scoring overlays with a real-time clock | Medium | Team | Overlay updates automaticcally during live games
Allow users to generate sharebale clips during streams | High | End Users/Sports Teams | Users an easily share video clips across social media channels
Requirement | Priority | Stakeholder | Acceptance Criteria
Streaming should have a latency of less than 5 seconds | High | End users/Sports Teams | Latency verified during live game broadcasts
Application should support both IOS and Android devices | High | Team | Application successfully launched and tested on both platforms
Functional Requirements:
PROJECT REQUIREMENT
Non-Functional Requirements:

## Slide 10
  Project Objectives:
    Provide a cloud-based streaming solution that simplifies live sports broadcasts.
    Ensure that the software is intuitive for parents and volunteers to set up and use.
    Integrate features like scoring overlays, remote scoring, and real-time clip sharing.
  In-Scope Items:
    Cloud streaming solution development.
    Creation of mobile apps (iOS and Android).
    Integration of overlays, scoring system, and sponsor logo display.
    24x7 support for all users.
  Out-of-scope Items:
    Custom game analytics tools.
    Advanced video editing functionalities.
    Hardware development (beyond standard cameras and tripods).
  Assumptions:
    Adequate internet bandwidth will be available for all users during live broadcasts.
    Hardware setup will be completed by volunteers with minimal training.
  Constraints:
    The project must remain within the $10 Million budget limit.
    Project completion is required before the start of the sports season (specific date).
PROJECT SCOPE

## Slide 11
Task | Task Name | Duration | Dependencies
1 | Project Start | 1 day | None
2 | Requirements gathering | 5 days | task 1
3 | Platform design | 15 days | task 2
4 | App design | 10 days | task 2
5 | Streaming Engine Development | 20 days | task 3
6 | App Development | 40 days | task 4
7 | Key Feature Integration | 15 days | task 5
PROJECT SCHEDULE

## Slide 12
Task | Task Name | Duration | Dependencies
8 | international regulation approval | 70 days | task 5, task 6
9 | platform testing | 10 days | task 5
10 | App testing | 10 days | task 6
11 | final debugging and bug fixing | 10 days | task 5, task 6, task 7
12 | Marketing and prelaucnh campaign | 15 days | task 8, task 11
13 | final review and approval | 5 days | task 11
14 | Product launch | 1 day | task 13
PROJECT SCHEDULE CONTINUED

## Slide 13
1. Identifying Critical Tasks:
2. Task Dependencies:
3. Critical Path Visualization
System Development | System Development must be completed before the platform is tested.
Regulatory Approvals (International) | Regulatory Approvals are a pre-requisite for launching the platform in international markets.
Platform Testing and Launch | Marketing & Launch are dependent on both system completion and regulatory approval.
CRITICAL PATH ANALYSIS
The critical path includes Platform Design, System Development, Testing, and Regulatory Approvals. If any of these tasks are delayed, the overall project timeline will be delayed.

## Slide 14
GLOBAL ELEMENT
1. International Time Zones:
Coordination with global teams across different time zones (e.g., USA, Europe, Asia) needs to be accounted for. This impacts both project development and international regulatory approvals.
Ensure task handovers are smooth and well-planned between different teams working in various time zones.
2. Regulatory Approvals (Global)
Regional Differences: Different countries have distinct regulatory requirements (e.g., GDPR compliance in the EU). Delays in getting approvals from certain countries may push back the launch in those regions.
Buffer Time: Allocate extra time for communication with regulators in different countries, allowing for possible delays in responses and documentation requirements.
3. Logistics and International Considerations
Depending on where the product is marketed, certain countries may have localization needs (e.g., language translations, local partnerships). Factoring in these global elements can impact timelines for marketing and deployment in specific regions.

## Slide 15
BUDGET ESTIMATION
1.Development Costs:
Web platform development: $500,000 (including UX/UI design, testing)
Mobile app (if applicable): $400,000
Technology stack (servers, cloud storage, etc.): $200,000/year
2. Marketing Costs:
Digital marketing (SEO, social media ads, PPC): $100,000/month
Content creation (photography, videography, blogs): $50,000/month
3.International Considerations:
Tariffs, shipping costs for any physical products: Estimated at 5-10% of sales.
Currency exchange fluctuations: Build in a 3-5% buffer for exchange rate variations.
Total Estimated Budget: $10 million
(Development: $900,000, Marketing for first year: $1.8 million, Miscellaneous/Buffer: $100,000)

## Slide 16
COST BASELINE
The cost baseline is the approved version of the project budget, including all costs for each stage of the Digital Arena development, which can be monitored and controlled.
Initial Costs (Development): $900,000
Operational Costs (Marketing, Tech Maintenance): $2 million/year
Tracking: Use project management software like Asana/Trello with budget tracking tools.
Change Control: Any changes to the cost baseline must go through a formal approval process, ensuring they are justified and within the project scope.

## Slide 17
FUNDING REQUIREMENT
Initial Investment: $900,000 for web/app development.
Ongoing Costs: $2 million/year for digital marketing, maintenance, and international fees.
Potential Funding Sources: Internal funding
Angel investors or venture capital
Bank loans or business grants (especially for startups with an international presence)

## Slide 18
GLOBAL ELEMENT
Tariffs and Shipping: If shipping physical goods (like sports gear), tariffs could range from 5-10%, depending on the countries involved.
Currency Exchange: Build a 3-5% buffer into international sales to account for fluctuations in currency exchange rates.
Logistics Costs: Include estimates for international shipping costs, likely to vary between $10-30 per unit depending on regions.

## Slide 19
RESOURCE MANAGEMENT PLAN
Human Resources Allocation:
  Project Manager: Full-time throughout the project to oversee tasks.
  Development Team: Cloud streaming developers, app developers, and integration team work full-time during the development phases.
  Quality Assurance Team: Part-time for platform and app testing.
  Marketing Team: Work full-time only after development. Primarily for pre-launch and campaign management.
  Regulatory Consultant: Part-time for international compliance.
Material Resources Allocation:
  Development Tools: Cloud Infrastrucutre, mobile SDKs, third-party APIs.
  Testing Environment: Servers for platform and app testing.
  Marketing Tools: Content management platforms, ad platforms for pre-launch campaigns.

## Slide 20
COMMUNICATION PLAN
Communication Channels:
  Project Management Tools: Use tools like Jira, Asana, or Microsoft Projects for task management and progress tracking.
  Video Conferencing: Use Zoom, Google Meets, or Microsoft Teams for weekly team meetings across time zones.
  Instant Message: Slack or Teams for daily updates.
  Email: Formal communications, especially for legal, regulatory, and marketing updates.
Meeting Schedule:
  Weekly Team Meetings: Synchronized across time zones. Rotate meeting times to accomodate various teams.
  Daily Standups: For development teams, use asynchronous communication for those in different time zones.
  Monthly Steering Meetings: Executive team to review project progress.
Global Considerations:
  Language Barriers: Provide project documentation in English and local languages if needed.
  Cultural Sensitivity: Be aware of holidays, weekends, and working styles across countries to minimize disruptions.

## Slide 21
Risk | Likelihood | Impact | Mitigation Strategy
International Regulatory Delays | High | High | Engage legal experts early for each region. Allow buffer time in schedule
Supply Chain Disruptions | Medium | High | Source alternative suppliers, maintain inventory of critical components
Geopolitical Instability | Medium | High | Monitor geopolitical developments and establish contingency plans.
Data Privacy Compliance | High | Medium | Work with compliance experts to audit data practices early.
Cultural Miscommunication | Medium | Medium | Conduct cross-cultural training for teams. Use visuals in documentation.
Key Personnel Unavailability | Medium | High | Cross-train team members. Keep detailed process documentation.
Technology Failures | Low | High | Regular backups, load testing, and cloud redundancy.
Currency Exchange Fluctuations | Medium | Medium | Hedge against exchange rate fluctuations for payments.
RISK MANAGEMENT PLAN
Risk Register:

## Slide 22
RISK MANAGEMENT PLAN CONT.
Mitigation Strategies:
  Early legal Consultation: Engage with legal teams early for GDPR, COPPA, and international broadcasting approval.
  Supply Chain Monitoring: Partner with multiple suppliers and maintain a buffer of key supplies to prevent delays.
  Cross Training: Ensure multiple team members are capable of taking over critical roles if someone becomes unavailable.
  Backup Systems: Cloud redundancy for key infrastrucutre to minimize downtime due to technology failures.
Global considerations:
  Geopolitical Risks: Regularly assess the stability of key regions for the supply chain and regulatory approval.
  International Supply Chain: Monitor global logstics trends and adjust timelines and sourcing strategies as needed.

## Slide 23
  Resource Acquisition (Month 1)- Based on the following key task assignments for teams, human and financial resources will be acquired in phases, teams formed & managed, and deliverables achieved as planned earlier.
  Adequate human and financial resource acquisition precedes product development.
  Engineers, UI designers, and functional leaders will be recruited through recruitment campaigns. Employees will be assigned to planned project teams based on regions, and teams managed through conflict resolution and negotiation techniques by Project Manager and Team Leaders to ensure effective product development.
EXECUTION OUTLINE
  Product Development Team- interface design and technology development
  Regulatory & Legal team- contract reviews, copyright compliance, international regulations adherence & obtaining broadcasting approvals
  Marketing team- create brand awareness and achieve product sales pre and post launch
  Payroll team- to oversee financial transactions and payments due
  Project Management team- project planning and execution

## Slide 24
  Managing teams- International developers will be managed by regional team leaders ensuring cultural adaptation (work styles accommodation, festivals celebrations and holidays) and accommodating time differences via scheduled meetings on Google Meets and asynchronous communication on emails.
  Requisite funds of $9, 00,000 for product development will be gathered through planned funding sources- VC firms and individual investors. Finances will be allocated across regional teams based on need and phase of development.
EXECUTION CONT.
  Product Development & Testing (Month 2-5)- The website, and iOS & Android applications will be developed by the engineering and UI design employees across global teams using GitHub for development collaboration, Slack for daily communication, emails for regular update sharing, and weekly scheduled virtual meetings.
  Subsequent integration of Overlays, Scoring System, and Sponsor Logo display feature will be carried out following successful streaming platform development. Application development depends on interface design completion, and functional features development depends on website & applications completion.

## Slide 25
EXECUTION CONT.
  Product Testing- The technology will be tested and quality reports, evaluation documents & change requests will be created to ensure quality standards as planned, and any changes implemented via the planned change control process.
  Stakeholders including the investors and team members will be updated on product status through Video Conferencing and Emails, handling time-zone and cultural differences as per communications plan, and stakeholder register will be updated regularly.
  Team leaders will be responsible for implementation success of these features. Any risks encountered will be tackled with the risk management plan and added to risk register; lessons learned will be added to the lessons learned register during this technology development phase and shared across teams.
  Feature development by global teams will utilize handovers to help meet time deadlines. Round the clock work through communication on emails, Slack, and Teams will further support development efficiency .
Product development cont.-

## Slide 26
  Marketing (Month 7)- $1.8M funds will be acquired for first year marketing phase needs. Another round of resource acquisition will create the marketing team, with international partners including social media influencers selected virtually and advertising adapted in local languages and preferences to ensure global success. Digital marketing- SEO, Social Media ads, and PPC will be utilized to create brand awareness before product launch. Target- establishing broadcasting partnerships with sports organizations and university leagues.
  Customer Support team will be created through recruitment for the office in US and through outsourcing agreements in international markets, following more financing for this phase. The customer support teams will be trained on product technology and cultural sensitivity by regional heads and team members via in-person meets and virtual meetings.
EXECUTION CONT.
  Regulatory approvals (Month 6)- This phase follows successful product development and testing, and is a dependency for marketing and product launch phases. Regulatory and legal consultants will be onboarded for contract reviews, copyright compliance, adhering to international regulations, and getting the GDPR, COPPA, other international broadcasting approvals on time, utilizing the allocated buffer time to accommodate any delays due to distinct international requirements and procedures.

## Slide 27
  Product Launch (Month 8)-
  Final Review and stakeholder approvals will be conducted before product launch to ensure adherence to the project management plan and meeting the deliverable needs as per planned standards- Scope Validation.
  Product launch will be conducted in phases, targeting more dominant markets of North America first, monitoring the live streaming functionality and the functional features of overlays, scoring system and clip sharing, followed by gathering user feedback and refining features for better user experience.
  Post-launch & Operations (Month 9-12)-
  Further product launch will be carried out in Asia, Africa and Latin America following any suitable changes to the product through formal procedures. Stakeholders including the investors, teams, and customers including schools/colleges and professional and recreational sports teams will be engaged through regular emails, virtual meets on planned platforms, and face-to-face meetings when needed.
  Following successful launch and product sales, further financing of $2M per year will be utilized for ongoing operational costs involved in product maintenance and improvement, marketing, and international fees associated with tariffs and logistics.
EXECUTION CONT.